## Sheet1
Risk | Level of risk | Likely Hood of happening | Risk Prevention | In the event of Risk happening
Hard drive with data from observations and questionares breaking/Corrupting the data | Severe | Unlikely however there is always the potential of this happening | Backup the data from tests aswell as store the data on multiple hard drives as this will help to ensure the project does not come to a halt | In the event of this happening, I would Try to recover the data if that is possible at all. If not then I would attempt to conduct more tests deppending on the amount of time left after informing the participants whose data it was, are informed of what has happened
Software for Development Runs into an issue with loading the project | Medium | Unlikely however there is always the potential of this happening | Backup the project files as this will help to ensure the project does not come to a halt. As well as this saving frquently and keeping multiple versions. | If this happens The first thing that will be done is the check the rest of the project to see if anything else is broken. Next will be to restore the latested version and see how far back it is.
Data relating to the project is deleted i.e software files | Medium | Unlikely however there is always the potential of this happening | Backup the project files as this will help to ensure the project does not come to a halt | If this happens The first thing that will be done is the check the rest of the project to see if anything else has been deleted as well. Next will be to restore the latested version and see how far back it is.